## Sheet1
Hospital Information Management System
Activity | Start Date | End Date | Duration | 45901 | 46134
Project Proposal | 2025-09-01 | 2025-10-01 | 30
Software Requirment Specification (SRS) | 2025-10-01 | 2025-10-20 | 19
Document Design | 2025-10-20 | 2025-12-15 | 56
Database & Knowledge Base Development | 2026-01-01 | 2026-01-07 | 6
Speech-to-Text & Speaker Diarization Setup | 2026-01-08 | 2026-01-14 | 6
Entity Extraction & Data Filtering | 2026-01-15 | 2026-01-28 | 13
Doctor Validation Workflow & Automated Note-Making | 2026-01-29 | 2026-02-11 | 13
Admin Dashboard Development | 2026-02-12 | 2026-02-25 | 13
Doctor Dashboard Development | 2026-02-26 | 2026-03-11 | 13
Patient Portal | 2026-03-12 | 2026-03-18 | 6
Security, Privacy & Compliance Implementation | 2026-03-19 | 2026-03-25 | 6
Testing | 2026-03-26 | 2026-04-01 | 6
Deployment & Staff Training | 2026-04-02 | 2026-04-08 | 6