## Sheet1
Hospital Information Management System
Activity | Start Date | End Date | Start | Week Labels | Duration | 46042 | 45931
Week 1 : Requirement Gathering & Project Planning | 2025-10-01 | 2025-10-07 | 1 | Week 1 | 1
Week 2 : System Architecture & Workflow Design | 2025-10-08 | 2025-10-14 | 2 | Week 2 | 1
Weeks 3–4 : Database & Knowledge Base Development | 2025-10-15 | 2025-10-28 | 3 | Week 3 | 2
Weeks 5–6 : Speech-to-Text & Speaker Diarization Setup | 2025-10-29 | 2025-11-11 | 5 | Week 4 | 2
Weeks 7–8 : Entity Extraction & Data Filtering | 2025-11-12 | 2025-11-18 | 7 | Week 5 | 2
Weeks 9–10 : Doctor Validation Workflow & Automated Note-Making | 2025-11-19 | 2025-11-25 | 9 | Week 6 | 2
Week 11 : Admin Dashboard Development | 2025-11-26 | 2025-12-09 | 11 | Week 7 | 1
Week 12 : Doctor Dashboard Development | 2025-12-10 | 2025-12-16 | 12 | Week 8 | 1
Week 13 : Patient Portal | 2025-12-17 | 2025-12-30 | 13 | Week 9 | 1
Week 14 : Security, Privacy & Compliance Implementation | 2025-12-31 | 2026-01-06 | 14 | Week 10 | 1
Week 15 : Testing | 2026-01-07 | 2026-01-13 | 15 | Week 11 | 1
Week 16 : Deployment & Staff Training | 2026-01-14 | 2026-01-20 | 16 | Week 12 | 1